Discussion document for ECOSTAT meeting 1-2 October 2008

Author: Sandra Poikane (JRC)

24 September 2008

The purpose of WFD Intercalibration work programme 2008 - 2011 is to fill all the gaps of the IC exercise in time for the second River basin management plans.

The first phase of the intercalibration has been carried out following the timetable included in the CIS Guidance Document No. 14 “Guidance on the Intercalibration Process 2004-2006”, published in 2005. For the second phase that has now just been initiated there is a need for an update of the timetable guidance, taking into account the experiences of the first phase and the work programmes of GIGS and BQE groups

This discussion document gives a starting point for the development of more detailed and practical timeframe.

General timetable and reporting for the intercalibration work programme 2008-2011

The purpose of the work programme 2008-2011 is to fill all the gaps of the intercalibration exercise in time for the second river basin management plans.

The proposed timetable (Figure 1) is constrained by the deadline to finalise Intercalibration Decision by December 2012, this requires completing the technical work in June 2011.

The proposed timetable contains following steps:

- ECOSTAT meetings are hold 2 times/year, GIGs prepare the progress reports which are agreed at ECOSTAT and further summarised and reported to the Strategic Coordination Group;

- There are IC results expected by 2009 which will be compiled at IC report  by the June 2010, other results are expected by 2010 and 2011 (see Table 1);

- The final IC results will be compiled at IC report by the end of 2011;

- Formal adoption of the new results will take place in 2012.

Fig.1. General Intercalibration timetable 2009-2011, including GIG Milestones (M1-M5),  WG ECOSTAT meetings and  IC reports.

The expected results can be divided in 3 parts:

- Results 2009: Rivers Central/Baltic: Macroinvertebrates and Macrophytes; River Alpine: Macrophytes; Rivers Eastern Continental: Macroinvertebrates, Macrophytes and Phytobenthos, Rivers Fish – all GIGs;

- Results 2010: Lakes Alpine – Macroinvertebrates, Lake Mediterranean – Phytoplankton;

- Results 2011: Most of the final results will be achieved 2011-2012 (see Table 1)

So there are 3 flows of the results with different timetables

- Results 2009:

  - M1 (March 2009) Development and application of Boundary setting protocol (including principles to set reference conditions),  identification of inconsistencies within the GIG;

  - M2 (October 2009) Final GIG report, including description of national assessment methods, boundary setting protocol, IC process and results.

- Results 2010:

- M1 (March 2009): Development of Boundary setting protocol (including principles to set reference conditions), agreement on IC option, common metrics, data needs, action plan;

- M3 (March 2010):  Compilation of dataset, application of Boundary setting protocol, identification of inconsistencies within the GIG;

- M4 Final GIG report, including description of national assessment methods, boundary setting protocol, IC process and results.

- Results 2011:

- M2 (October 2009): Development of Boundary setting protocol (including principles to set reference conditions), agreement on IC option, common metrics, data needs, action plan;

- M4 (October 2010) Compilation of dataset, application of Boundary setting protocol, identification of inconsistencies within the GIG;

- M5 (May 2011): Final GIG report, including description of national assessment methods, boundary setting protocol, IC process and results.

Table 1. Expected results of River / Lake Intercalibration continuation 2008-2011.

|  | RIVERS |
| --- | --- |
| GIG / BQE | Phytoplankton | Macro invertebrates | Macrophytes | Phytobenthos | Fish |
| ALP |  | Completed | Results 2008 | Completed | Results 2009 |
| CB |  | Completed, additional results 2009 | Draft results 2008, cont 2009 | Partly completed, proposal for cont. 2008 |  |
| EC |  | Completed, additional results 2009 | Results 2009 | Results 2009 |  |
| MED |  | Completed, additional results 2011 | Results 2011 | Completed, additional results 2009 ? |  |
| NOR |  | Completed for general pressure Contin. for acidification Results 2009 | Not started, feasibility will be evaluated 2009 | Completed, possible cont. 2009 |  |
|  | LAKES |
| ALP | Parly completed, new results 2012 | Results 2010 | Partly completed, new results 2012 |  | Results 2011 |
| CB | Parly completed, new results 2011 | Results 2011 | Partly completed, new results 2011 |  |  |
| EC | Results 2011 | Results 2011 | Results 2011 |  |  |
| MED | Parly completed, new results 2009-2010 | Results 2012 | Results 2012 |  |  |
| NOR | Parly completed, new results 2011 | Results 2010/2011 | Parly completed, new results ? |  |  |